AI Features for LMS — Phase 1 MVP

AI Engineering Team: Quick Wins & Delivery Plan

June 02, 2026

# 1. What the AI Engineering Team Delivers

5 quick wins delivered over 6 weeks. Each is independently testable and demoable. Services are Python microservices running on Azure Container Apps.

| # | Quick Win | What It Does | Why First | Effort | Week |
| --- | --- | --- | --- | --- | --- |
| 1 | LLM Gateway | Single entry point for all AI model calls. Routes to fast model (GPT-4o-mini) for chat or capable model (GPT-4o) for content generation. Tracks usage per customer organization. Enforces budget caps. | Everything else calls this. No dependencies. Standalone service. | 1 week | Week 1 |
| 2 | Content Indexing | Converts course lessons into searchable AI format. Splits text into chunks, generates embeddings (AI-friendly representations), stores in Azure AI Search with metadata (which course, lesson, section). | Every grounded AI feature needs indexed content. Can be tested before platform is ready. | 1-2 weeks | Week 2-3 |
| 3 | Learner Profiles | Stores what we know about each learner: skills, goals, role, experience level. Simple create/read/update service. Used later for personalized paths and recommendations. | Simple CRUD. No AI dependency. Builds foundation for personalization. | 1 week | Week 2-3 |
| 4 | Search & Retrieval | Given a question and a lesson, finds the most relevant sections of content. Enforces customer data isolation. Returns source citations (lesson title, section, timestamp). | Thin wrapper around AI Search. Enables the Tutor. | 1 week | Week 3-4 |
| 5 | In-Lesson Tutor | Learner asks a question while studying — gets an answer grounded in the lesson material with citations proving where the answer came from. Conversation history kept for 30 days, learner can delete anytime. | The signature feature. What learners will actually use. First demo in Week 4. | 1-2 weeks | Week 4-6 |

# 2. Development Timeline

Parallel tracks start Week 1. Quick wins (QW1-5) complete by Week 6. Remaining 7 features build on this foundation in Weeks 5-8.

| Feature | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LLM Gateway (QW1) | Build |  |  |  |  |  |  |  | Quick Win |
| Content Indexing (QW2) | Build | Build |  |  |  |  |  |  | Quick Win |
| Learner Profiles (QW3) | Build |  |  |  |  |  |  |  | Quick Win |
| Search & Retrieval (QW4) |  |  | Build |  |  |  |  |  | Quick Win |
| In-Lesson Tutor (QW5) |  |  |  | Build | Build |  |  |  | Quick Win |
| Post-Activity Insights |  |  |  |  | Build |  |  |  |  |
| Learning Paths |  |  |  |  | Build | Build |  |  |  |
| Assessment Generation |  |  |  |  | Build | Build |  |  |  |
| Course Recommendations |  |  |  |  |  |  | Build | Build |  |
| Platform Assistant |  |  |  |  |  |  | Build | Build |  |
| Quality Checks |  |  |  |  |  |  |  | Build |  |
| Fail-Graceful Handling |  |  |  |  |  |  |  | Build |  |

First demo: Week 4 (LLM Gateway + Indexing + Search + Tutor = learner asks a question, gets an answer with citations from the course material).

MVP quick wins complete: Week 6 (all 5 quick wins delivered and testable).

Full Phase 1 complete: Week 8-10 (all 12 features including admin tools, recommendations, and production readiness).

# 3. Feasibility Assessment

| Factor | Assessment | Confidence |
| --- | --- | --- |
| Technical complexity | Azure AI Search handles the hard parts (chunking, embeddings, vector search). Our code is mostly orchestration and configuration. The Tutor is approximately 500 lines of Python. | High |
| Team capacity | 3 parallel tracks in Week 1 (Gateway, Indexing, Profiles). All are independent — no coordination overhead. 8-10 weeks total for one AI engineer. | High |
| Dependencies on platform team | Minimal. Only need: content files in Blob Storage and a skill taxonomy list. All AI services can be built and tested standalone via HTTP endpoints before platform UI exists. | High |
| Azure service availability | All services are generally available. Risk: AOAI model capacity in target region (mitigated by provisioning in Week 0). | Medium |
| Cost | Pilot scale (2-3 organizations). Azure Container Apps scale-to-zero eliminates idle costs. GPT-4o-mini is cost-efficient for chat. GPT-4o used sparingly for content generation. | High |

# 4. What the Platform Team Must Provide

These inputs are required from the platform engineering team. Items marked "Week 0" are needed before AI development starts. Items marked with a week number are needed by that week.

| # | Input Needed | Required By | Why |
| --- | --- | --- | --- |
| P1 | Content files (lesson text, transcripts) uploaded to Blob Storage | Week 1 | Indexing pipeline needs content to index. Can be sample content initially. |
| P2 | Skill taxonomy — list of valid skills learners can select | Week 2 | Learner Profile Service validates skills against this list. Can be a static file initially. |
| P3 | Course and lesson metadata (IDs, titles, module structure) | Week 3 | Indexing needs course/lesson IDs for metadata. Search needs module structure for scope filtering. |
| P4 | Catalogue data (courses, tags, prerequisites, estimated effort) | Week 5 | Learning Paths and Recommendations need course data to generate suggestions. |
| P5 | Quiz result data (scores, per-question correctness, lesson context) | Week 5 | Post-Activity Insights needs quiz results to generate coaching feedback. |
| P6 | Learner enrollment and progress data | Week 6 | Platform Assistant needs progress data to answer "How far am I?" questions. |
| P7 | Admin review UI (for approving generated assessments) | Week 6 | Assessment Generation needs a UI where admins can review, approve, reject, or edit questions. |
| P8 | Learner-facing UI surfaces (chat box, dashboard widgets, quiz results page) | Week 4 | Tutor and other features need UI surfaces for learners to interact with. AI team provides APIs only. |

# 5. Blockers & Risks

All HIGH severity items must be resolved before development starts (Week 0).

| Risk | Severity | Impact if Not Resolved | Mitigation |
| --- | --- | --- | --- |
| Azure OpenAI models not available in target region | HIGH | Cannot generate any AI responses. Project blocked. | Provision AOAI in Week 0. Identify backup region. |
| AI Search tier cannot support vector search | HIGH | Cannot index or search content. All grounded features blocked. | Provision Standard S1 in Week 0. Verify quota. |
| Platform team delays on content and data delivery | HIGH | AI services built but cannot be tested with real data. | AI team tests with synthetic content. HTTP endpoints work without platform UI. |
| Tutor response too slow (target: under 5 seconds) | MEDIUM | Poor learner experience. May need to adjust model or chunk size. | Monitor from Day 1 with Application Insights. Tune as needed. |
| No real course content for development | MEDIUM | Cannot validate retrieval quality with real material. | Use fabricated content for development. Real content for pilot. |
| Stakeholders want open-source models in Phase 1 | LOW | Scope creep. Delays Phase 1 delivery. | Gateway supports any model from Day 1. Adding a model is config, not code. Phase 2 deliverable. |

# 6. Delivery Summary

| Metric | Value |
| --- | --- |
| Quick wins delivered by AI team | 5 |
| Quick win delivery window | Week 1 to Week 6 |
| First working demo | Week 4 (In-Lesson Tutor with grounded answers and citations) |
| Total features in Phase 1 | 12 (5 quick wins + 7 additional features) |
| Total effort | 8-10 weeks |
| AI team size | 1 AI Engineer |
| Platform team inputs needed | 8 items (see Section 4) |
| Blockers to resolve immediately | 3 HIGH severity (AOAI capacity, AI Search tier, platform content availability) |
| Technology stack | Azure OpenAI, Azure AI Search, Azure Container Apps, PostgreSQL, Redis, Blob Storage, Service Bus |